# Project Plant Pals Roadmap: [Name]

Last updated: 11/11/2025

Goal #1: Increase online business-to-consumer sales by 20% YoY

Goal #2: Increase holiday sales to existing customers by 8% over last year by December 31, 2021

| Our approach is to Increase online business-to-consumer sales by 20% YoY through: - Add inventory to PPP - Increase annual upsells through marketing new inventory - Replace online storefront with new friendlier UI | Our approach is to Increase holiday sales to existing customers by 8% over last year by December 31, 2021 through: - Add inventory to PPP - Increasing training around how to nurture current customers - Increasing the strength of leads coming into the funnel and tightening up your qualifying processes |
| --- | --- |

## High-Level Project Overview:

By Q3 2021, Project Plants Pals will launch a new storefront with additional inventory, just in time for the holiday season. The new inventory should be easily bundlable with the PPP existing inventory; facilitating upsells that delight our users. The new site will work for business-to-consumer and business-to-business sales.

|  | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 |
| --- | --- | --- | --- | --- |
| Key Milestones Owner(s): | Finalize inventory for the holiday season. 28 February 2021 | Get sign-off on Go to Market Strategy 1 May 2021 | SOFT launch of refreshed online store and holiday inventory with new offerings 1 September 2021 ⇒ PR: Press releases ⇒ Replace online storefront | Full launch of holiday inventory with new offerings 31 October 2021 ⇒ Targeted PR Push ⇒ UX fixes to online store front |
| Marketing Owner(s): | Complete 2020 Holidays competitor analysis Research new/emerging markets ⇒ Complete product testing -- user feedback surveys for new offerings | Get sign-off on Go to Market Strategy for new offerings + existing inventory (w. Sales) Sign off on inventory photographs and product summaries for website, e-newsletters, mailers, and catalog Refine marketing strategy ⇒ Research paid traffic ⇒ Test display ads strategy | Review display ads results and make a Go/No-Go decision Soft/Pre-launch PR Push ⇒ Press release ⇒ Ship mailers and catalogs Review CTR from marketing push | Optimize PR strategy for late holiday surge. Targeted PR Push ⇒ Display ads? ⇒ Social media posts ⇒ e-Newsletter |
| Sales Owner(s): | Complete 2021 projections/forecast of holiday sales (units) based on 2020 holidays sales Finalize suggestions for additional offerings/inventory Define measurement protocols (w. Product & Engineering) | Get sign-off on Go to Market Strategy for new offerings + existing inventory (w. Marketing) Sales Rep training: ⇒ How to nurture current customers ⇒ How to evaluate the strength of leads coming into the funnel ⇒ Expanding reps’ product knowledge to encourage up-sells/cross-sells Finalize pricing adjustments on all inventory Review Q4 KPIs with CEO | Sales previews/roadshows with Top Tier 2020 customers (Repeat business) ⇒ Close pre-order deals per targets Sales previews/roadshows with Top Tier New Customers ⇒ Build leads per targets | Sales previews/roadshows with Top Tier New Customers ⇒ Close new deals per targets Review KPIs for October, November, December (against actuals) in weekly reviews with CEO |
| Product & Engineering Owner(s): | Finalize requirements for updates to the online store Define measurement protocols (w. Sales) | Dev complete ⇒ Complete updates to online store to requirements ⇒ Implement measurement protocols (Complete UAT with Sales) Final bug fixes and complete QA testing | Replace online storefront Complete UX Audit ⇒ Review UX bugs ⇒ Propose Recommended Solutions ⇒ Scope to implement changes by 30 October 2021 | Complete sign-ff and testing for UX changes |